## Ongoing
Category/Goal | Objective | Actions | Updates | Budget | Completion Date
Parish Council Administration To comply with the law and keep the community informed | To ensure that the Parish Council administration is run in an efficient and timely manner, and that information is open and transparent | Publish Agendas, minutes and means of contacting the Council on the website and noticeboards.Calendar of meetings to be issued |  |  | Ongoing
Council governance, policies, & procedures To comply with the law | To ensure all Council policies and procedures are reviewed regularly and updated as necessary | Clerk to ensure review processes are in place |  |  | Ongoing
|  | All Councillors and staff to receive appropiate training | Cllrs Bryson, Sjollema, Hodges and Hobden have completed Councillor training. | Training | Ongoing
|  | To consider cloud based storage options | Clerk researching and seeking quotes | Subscriptions | Ongoing
|  | To redesign the website to ensure it meets the WCAG2.2 legal requirements | Clerk researching and seeking quotes | Website | Ongoing
Community To engage with and support the local community | Engage with the Community to help shape the Parish Council and Parish | Represent Council on other organisations and group meetings where possible Keep website and social media updated Quarterly Newsletter Encourage parishioners to attend Council meetings Consult with parishioners on ideas for new initiatives |  | Website | Ongoing
| Support or host events within the village which are inclusive for all | D-DAY 80 Celebration Remembrance Sunday Service | D-Day 80 event held 6th June 2024. Remembrance Service held annually | Events S137
| Support local charities and groups | Ensure donation policy is up to date Ensure donation requests are via the application form | Donations have recently gone to: Oars for Paws, Heybridge Primary PTFA, Essex & Herts Air Ambulance, Warm Hub, HB Rivercare, RBL, HB Defib Fund, Marie Curie, Friends of Heybridge Cemetery | Chair Allowance Donations | Ongoing
Community Safety To improve safety within the village | To reduce speeding traffic | Community Speedwatch Group 20's Plenty Campaign | Speedwatch volunteers trained and active since November 2023. Cllr Sjollema represents the Council on the 20's Plenty campaign. 20mph bin stickers purchased for Basin Road residents. | Chair Allowance | Ongoing
| To provide safer pedestrian access | Liase with MDC regarding installing a Pedestrian Access sign on the St George’s Road name sign | MDC have given permission. Await costings | Asset Maintenance | Ongoing
| To change the on-street parking regulations within the village |  | Application pack sent to SEPP - September 2024 |  | Ongoing - up to 12 months to hear back from SEPP
Planning To monitor development and planning within the village | To consider all planning applications which fall within, and impact upon the Parish |  |  |  | Ongoing
| To ensure Village Design Statement is still relevant | Consider a more comprehensive re-write of the document. | Working Group has requested MDC endorse the addendum as an interim measure. |  | Ongoing
| To consider the need for a Neighbourhood Plan | Determine the need for a Neighbourhood plan. Discuss process and costs. | Working Group set up to research |  | Ongoing
Assets To maintain and enhance assets | Village Sign | To look into options to make the pole safer due to the current rotting. |  | Asset Maintenance | Ongoing
| Green Gym | Consider if the Council wish to go ahead with the project. | Consulted village and was very close on results. |  | Ongoing
| Goal Posts To replace the old goal posts on St George's Field | To seek installation costs. Awaiting delivery | B. Riches to carry out inspections. License Agreement imn place with MDC. Goal Posts purchased | Asset Maintenance | Ongoing
United Reformed Church | To keep the old chapel in the Community |  | MDC rejected Asset of Community Value application |  | Ongoing
Daisy Meadow Car Park | Grounds Maintenance To ensure regular maintenance and emptying of the litter and dog bins | Review the current Grounds Maintenance Schedule |  | Grounds Maintenance | Ongoing
| Drain Cleaning To ensure the drains are kept clear | Consider how often the drains need cleaning | Drain cleaned November 2023 | DMCP Asset Maintenance | Ongoing
| Planting | Plans for DM Garden underway - Need to discuss water supply and Phase 2 plans. | Phase 1 plan and materials confirmed. Clerk to order. HRS contracted. | DMCP Planting | Ongoing
| Public Toilets To consider installing public toilets within DMCP | DM Working Group need to meet to discuss design requirements, location etc. | Early engagement is on the Tender website - deadline 12th February 2025 | DMCP | Ongoing
| EV Chargers To consider the need for EV chargers | Ascertain whether or not planning permission is required. Is there a want/need for them? Research types of chargers and costs. | Cllr Bryson and Clerk met with MDC - Report to be given to Council | DMCP | Ongoing
| Pay on Exit System To consider moving to a pay on exit system/changing operator | Discuss the recent proposal from Smart Parking. Discuss whether to meet in person with the other operators. |  | DMCP | Ongoing

## Completed
Category/Goal | Objective | Actions | Updates | Budget | Completion Date
Daisy Meadow Car Park | Felling of 6 Leylandii |  | Planning permission granted. Blackwater Tree Specialists contracted. | DMCP
| Resurface Access Road |  | No planning application required. Tender proccess followed. Design provided by Haydn Evans Ltd. Camway contracted. | DMCP | 17th May 2024
Land Adjacent St Georges Church | To obtain the land |  | Adverse Possession application submitted and granted. Offical deeds received. | Legal
Noticeboard near Jolly Sailor | To cleary identify the noticeboard as the Councils |  | Heybridge Basin Parish Council sign purchased from Blackwater printing and attached to noticeboard. | Asset Maintenance
Bench near Bus Shelter | To repair the bench |  | Slats repaired. Older slats sanded and varnished to match | Asset Maintenance
Basketball Hoops | To replace the old Basketball Hoop - St George's Field |  | Awarded £500 grant. B Riches to carry out inspections. License Agreement in place with MDC. Hoop purchased and installed | Tesco Community Champions Grant Asset Maintenance | 2024-12-01